## Sheet1
| SP-1 | SP-2 | SP-3 | SP-4 | SP-5 | SP-6 | SP-7 |  | SP-8 | SP-9 | SP-10 | SP-11 | SP-12 | SP-13 | SP-14 | SP-15 | SP-16 | SP-17 | SP-18 | SP-19
Organisaton | [7 empty] | EASTER HOLIDAYS
Specification and planning realisation
Dataset Generation
Research of existing methods of sound localization
Research of existing datasets and sound simulation software
Creation of a tool to transform of a sound into a spectrogram
Create 3D models of different environments
Generate a dataset using the sound spatialization software
Model Creation
Research and study of existing models | bar: SP-8 to SP-9
Design and implementation of the model | bar: SP-8 to SP-9
Train the model on the generated dataset | bar: SP-8 to SP-9
Evaluate the model and check its accuracy | bar: SP-8 to SP-9
Model validation
Documentation
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Documentation | [7 empty] | EASTER HOLIDAYS
Specification and planning realisation
Report
Dataset Generation
Research of existing methods of sound localization
Definition of the baseline | bar: 8 to 9
Research and creation of baseline datasets and sound simulation software | bar: 9 to 10; 14 to 15
Creation 3D models of different environments | bar: 9 to 10; 14 to 16
Generate a dataset using the sound spatialization software | bar: 9 to 10; 14 to 16
Evaluate the dataset and make sure it is suitable for training | bar: 9 to 10; 14 to 16
Model Creation
Research and study of existing models | bar: 10 to 11; 14 to 16
Design and implementation of the model | bar: 10 to 11; 14 to 16
Train the model on the generated dataset | bar: 11 to 12; 15 to 17
Evaluate the model and compare its accuracy | bar: 11 to 12; 15 to 17
Model validation
Test the model against real-world data | bar: 11 to 12; 16 to 17
Evaluate the model against environmental changes | bar: 8; 11 to 12; 17
Compare the results against the baseline | bar: 8; 11 to 13; 17 to 19
Research and study of adversarial attack that could be applied to this project | bar: 12 to 13; 17 to 19
Test the model against the adversarial attack | bar: 12 to 14; 17 to 19
Find ways to improve the model and limit attack vector | bar: 13 to 14; 17 to 19